## Sheet1
Final Product Backblog
# | Function/Screen | Feature | Function/Screen Details | Level* | In charge | Actual | Updated? | Details on update | SRS Section | SDS Section
1 | User Login | Common | This is scrren when user want to access the important part of the website have to do. User access with their created account or can go ahead and create a new one | Simple | HungTHHE140042 | Iter1 | No
2 | User Register | Common | This is the screen user want to access other parts of the website but does not already have username and password. Therefore they will have to enter their new username and password, come along with email and phone number | Simple | HungTHHE140043 | Iter1 | No
3 | User Reset Pasword | Common | This is the screen for user that have already created an acoount but does not remember username or password, they can enter the email and the website will send them new user and password via email | Simple | HungTHHE140044 | Iter1 | No
4 | Blog List | Common | Blog is the post who created by the marketing team, the advertise about new product, new promotion to user. Or just simply review about a product. With a title, author, date, thumbnail and a briefly descript about the product | Medium | HungDQHE140063 | Iter1 | No
5 | Blog Details | Common | Blog deital is the detailed part of one blog, Display any thing about the product, User can access this and see more about the product | Simple | HungDQHE140064 | Iter1 | No
6 | Permission Homepage | Security | Role permission can access to features at Homepage | Simple | DinhNLHE140992 | Iter1 | No
7 | Desgin Homepage | Public | This is the screen when user access the website the first time, can be aceess with or without and account. Display the header, footer of the website, and the body descript about promotions, category, featured product and brands of the store products | Simple | DinhNLHE140993 | Iter1 | No
8 | User Profile | Common | This is the backend part to manage user acess between, user, seller, marketing and admin. All have different acess, different use to the website | Complex | LongNTHE140955 | Iter1 | No
9 | Permission Dashboard | Security | Role permission can access to features at Dashboard | Simple | SangNQHE140244 | Iter1 | No
10 | Desgin Dashboard | Public | This is management screen. There is CRUD account, product, blog, faq,… | Simple | SangNQHE140245 | Iter1 | No
11 | Account management | Admin | This function is in dashboard. There is List, Create, Update, Delete accounts in systems | Complex | SonTNSE04223 | Iter1 | No
Note on G3: KienNT: Actual iteration when you have completed the function; N/A means incompleted
Note on H3: KienNT: You have updated the function in the last iteration?
Note on J3: KienNT: The name of section in the SRS (software requirement specification) document
Note on K3: KienNT: The name of section in the SDS (software design specification) document