## Backlog
Final Product Backblog
# | Function/Screen | Feature | Function/Screen Details | Level* | In charge | Actual | Updated? | Details on update | SRS Section | SDS Section
1 | User Login | Common | This is scrren when user want to access the important part of the website have to do. User access with their created account | Simple | HungTHHE140042 | Iter1 | No
2 | User Register | Common | This is the screen user want to access other parts of the website but does not already have username and password. Therefore they will have to enter their new username and password, come along with email | Simple | HungTHHE140043 | Iter1 | No
3 | Verify new register | Common | After registed success, a link by an email will send to user registed email. Access email to verify account. | Simple | HungTHHE140043 | Iter1 | No
4 | Post dashboard | Marketing | Post Dashboard is the post who created by the marketing team, the advertise about new product, new promotion to user. Or just simply review about a product. With a title, author, date, thumbnail and detail image and a briefly descript about the product - Allow the admin/marketing to search post by post's id, author, title, content - The list is sortable by post' id, author, title, content - From each post, the admin/marketing can choose to edit it - The page also have the button that allows the admin/marketing to create new post and delete post | Medium | SonTNSE04223 | Iter1 | No
5 | Homepage | Common | Homepage is welcome page, its display top discount product, newest product, popular products and latest post. Beside, header will change between user logged or not | Medium | DinhNLHE140992 | Iter1 | No
6 | Change Password | Common | This is screen to user change their password | Simple | HungDQHE140061 | Iter1 | No
7 | Profile Detail | Common | This is a screen which allows user to view their own profile information, including all personal information. | Simple | HungDQHE140062 | Iter1 | No
8 | Products List | Common | Show the paginated list of products (include products' id, thumbnail, title, category, list price, sale price). The user can filter the product by category, price or search by title | Simple | SangNQHE140244 | Iter1 | No
9 | Product Details | Common | Show detailed product information (thumbnail, title, attached images, description, quantity, list price, sale price), | Simple | SangNQHE140245 | Iter1 | No
10 | Users List | Admin | Show the paginated list of registered users (include users' id, username, password, email, role, status): - Allow the admin to search users by username, email, id - The list is sortable by users' id, username, password, email, role, status - The page also have the button that allows the admin to add new user and delete user | Simple | LongNTHE140954 | Iter1 | No
11 | User Details | Admin | Show detailed user information (user's id, username, email, mobile, role, status), from that allow the user to add new, view or edit user information - The admin can edit all information of the user | Simple | LongNTHE140955 | Iter1 | No
Note on G3: KienNT: Actual iteration when you have completed the function; N/A means incompleted
Note on H3: KienNT: You have updated the function in the last iteration?
Note on J3: KienNT: The name of section in the SRS (software requirement specification) document
Note on K3: KienNT: The name of section in the SDS (software design specification) document

## Iter1
Iteration 1
# | Function/Screen | Feature | Level | Function/Screen Details | In Charge | Status | Notes
1 | User Login | Common | Simple | This is scrren when user want to access the important part of the website have to do. User access with their created account | HungTHHE140042 | Done
2 | User Register | Common | Simple | This is the screen user want to access other parts of the website but does not already have username and password. Therefore they will have to enter their new username and password, come along with email | HungTHHE140043 | Done
3 | Verify new register | Common | Simple | After registed success, a link by an email will send to user registed email. Access email to verify account. | HungTHHE140043 | Done
4 | Post Management | Marketing | Medium | Post Dashboard is the post who created by the marketing team, the advertise about new product, new promotion to user. Or just simply review about a product. With a title, author, date, thumbnail and detail image and a briefly descript about the product - Allow the admin/marketing to search post by post's id, author, title, content - The list is sortable by post' id, author, title, content - From each post, the admin/marketing can choose to edit it - The page also have the button that allows the admin/marketing to create new post and delete post | SonTNSE04223 | Done
5 | Homepage | Common | Medium | Homepage is welcome page, its display top discount product, newest product, popular products and latest post. Beside, header will change between user logged or not | DinhNLHE140992 | Done
6 | Change Password | Common | Simple | This is screen to user change their password | HungDQHE140061 | Done
7 | Profile Detail | Common | Simple | This is a screen which allows user to view their own profile information, including all personal information. | HungDQHE140062 | Done
8 | Products List | Common | Simple | Show the paginated list of products (include products' id, thumbnail, title, category, list price, sale price). The user can filter the product by category, price or search by title | SangNQHE140244 | Done
9 | Product Details | Common | Simple | Show detailed product information (thumbnail, title, attached images, description, quantity, list price, sale price), | SangNQHE140245 | Done
10 | Users List | Admin | Simple | Show the paginated list of registered users (include users' id, username, password, email, role, status): - Allow the admin to search users by username, email, id - The list is sortable by users' id, username, password, email, role, status - The page also have the button that allows the admin to add new user and delete user | LongTNHE140954 | Done
11 | User Details | Admin | Simple | Show detailed user information (user's id, username, email, mobile, role, status), from that allow the user to add new, view or edit user information - The admin can edit all information of the user | LongTNHE140955 | Done

## Iter2
Iteration 2
# | Function/Screen | Feature | Level | Function/Screen Details | In Charge | Status | Notes
12 | Product Management | Seller | Complex |  | HungTHHE140042 | Doing
13 | Post list | Common | Simple | Show the paginated list of posts (include post's id, author, title, content, image, date). | SonTNSE04223 | Doing
14 | Post detail | Common | Simple | Show detailed post information (post's id, author, title, content, image, date), | SonTNSE04223 | Doing
15 | CMS Dashboard | Admin - Seller - Marketing | Simple | Analysis: Total product revenue, Product revenue in this month, Total success order, Amount of current pending order Revenue by day chart, Category have product success order chart | DinhNLHE140992 | Doing
16 | Product Review | Customer - Seller - Marketing | Medium | At product detail page, user can comment to review about product. Seller or Marketing can reply user's review. | HungDQHE140061 | Doing
17 | My Cart | Common | Simple | List all product user has add to cart. User also increase, decrese product amout or delete them. | SangNQHE140245 | Doing
18 | Add to Cart | Common | Medium | After click button "Add to cart" from Product page, that product will has been add to user cart. | SangNQHE140245 | Doing
19 | FAQ Management | Marketing | Medium | FAQs Dashboard is the FAQ who created by the marketing team, its frequently asked questions. Summary of questions from product review, marketing team will create FAQs - Allow the admin/marketing to search post by faq's id, author, title, content - The list is sortable by faq's id, author, title, content - From each post, the admin/marketing can choose to edit it - The page also have the button that allows the admin/marketing to create new FAQ and delete FAQ | LongNTHE140954 | Doing

## Iter3
Iteration 3
# | Function/Screen | Feature | Level | Function/Screen Details | In Charge | Status | Notes
20 | User Reset Pasword | Common | Simple | This is the screen for user that have already created an acoount but does not remember username or password, they can enter the email and the website will send them new user and password via email | HungTHHE140042 | Done
21 | Categories Management | Admin | Simple |  | SonTNSE04223 | Doing
22 | Promotion Code Management | Admin | Medium |  | DinhNLHE140992 | Doing
15 | FAQ list | Common | Simple |  | HungDQHE140061 | Doing
16 | FAQ detail | Common | Simple |  | HungDQHE140062 | Doing
24 | Cart Completion (Checkout) | Common | Medium |  | SangNQHE140245 | Doing
25 | Notifications Management | Admin | Medium |  | LongNTHE140954 | Doing

## Iter4
Iteration 4
# | Function/Screen | Feature | Level | Function/Screen Details | In Charge | Status | Notes
26 | About us | Common | Simple |  | HungTHHE140042 | Doing
| Auto send email | Common | Simple |  | HungTHHE140042 | Doing
27 | Order history | Common | Simple |  | SonTNSE04223 | Doing
28 | Order history detail | Common | Simple |  | SonTNSE04223 | Doing
29 | User Authorization | Security | Complex |  | DinhNLHE140992 | Doing
30 | Email Management | Admin | Medium |  | HungDQHE140061 | Doing
31 | Notification list | Common | Simple |  | LongNTHE140954 | Doing
32 | Notification detail | Common | Simple |  | LongNTHE140954 | Doing
33 | Order Management | Admin | Medium |  | SangNQHE140245 | Doing