## WR1
PROJECT REPORT
Group | Group 2 - SWp391.E-BL5
Week | <11/04/2022-15/04/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Create Baklog | Completed
2 | Create SRS | Completed
3 | Create SDS | Completed
4 | Design Database | Completed
5 | Design template website | Completed
6 | Create Github Repository | Completed | https://github.com/HungTHHE140042/SWP391.E-BL5_Group2
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Draw Context diagram | SonTN
2 | Draw Screen flow | SonTN
3 | Draw ERD | SonTN
4 | Draw package structure | HungTH
5 | Design database | DinhNL | SQL Server
6 | Create Github Repository | HungTH
7 | Design template website | HungTH
8 | Completion SRS | All members
9 | Completion SDS | All members
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Format again SRS, SDS | In Progress
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | User Login | 24/04/2022
2 | User Register | 24/04/2022
3 | Verify new register | 24/04/2022 | (Verify by send link to email)
4 | Post dashboard | 24/04/2022
5 | Homepage | 24/04/2022
6 | Change Password | 24/04/2022
7 | Profile Detail | 24/04/2022
8 | Products List | 24/04/2022
9 | Product Details | 24/04/2022
10 | Users List | 24/04/2022
11 | User Details | 24/04/2022
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | About Github, some members don't know how to use it | HungTH | 22,23/4/2022, Team will online meet to discuss and teach each other.
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C33: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue