## Backlog
Final Product Backblog
# | Function/Screen | Feature | Function/Screen Details | Level* | In charge | Actual | Updated? | Details on update | SRS Section | SDS Section
1 | User Login | Common | This is scrren when user want to access the important part of the website have to do. User access with their created account or can go ahead and create a new one | Simple | HungTHHE140042 | Iter1 | No
2 | User Register | Common | This is the screen user want to access other parts of the website but does not already have username and password. Therefore they will have to enter their new username and password, come along with email and phone number | Simple | HungTHHE140043 | Iter1 | No
3 | Verify new register | Common |  | Simple | HungTHHE140043 | Iter1 | No
4 | Post dashboard | Admin | Blog is the post who created by the marketing team, the advertise about new product, new promotion to user. Or just simply review about a product. With a title, author, date, thumbnail and a briefly descript about the product | Medium | SonTNSE04223 | Iter1 | No
5 | Homepage | Common | Homepage display hot product, new product, latest blog,… | Medium | DinhNLHE140992 | Iter1 | No
6 | Change Password | Common | This is screen to user change their password | Simple | HungDQHE140061 | Iter1 | No
7 | Profile Detail | Common | This is a screen which allows user to view their own profile information, including all personal information & avatar image. User can change profile detail by click in edit button to redirect in edit profile screen. User can view order history by click in order history button | Simple | HungDQHE140062 | Iter1 | No
8 | Products List | Common | Show the paginated list of products (include products' id, thumbnail, title, category, list price, sale price, featured, and status information): - The user can filter the product by category, status or search by title, brief info - Sortable by title, category, list price, sale price, featured, or status - From each product, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new product | Simple | SangNQHE140244 | Iter1 | No
9 | Product Details | Common | Show detailed product information (thumbnail, category, title, brief information, attached images, description, quantity, list price, sale price, flag to turn the featurning on/off, status), | Simple | SangNQHE140245 | Iter1 | No
10 | Users List | Admin | Show the paginated list of registered users (include users' id, full name, gender, email, mobile, role, status): - The admin can filter the users by gender, role, status - Allow the admin to seach users by full name, email, mobile - The list is sortable by id, fullname, gender, email, mobile, role, status - From each user, the admin can choose to view or edit it - The page also have the button/link that allows the admin to add new user | Simple | LongNTHE140954 | Iter1 | No
11 | User Details | Admin | Show detailed user information (avatar, full name, gender, email, mobile, role, address, status), from that allow the user to add new, view or edit user information - After adding, new generated login password would be email to the new user - The admin can only edit/update the role and status of the user | Simple | LongNTHE140955 | Iter1 | No
Note on G3: KienNT: Actual iteration when you have completed the function; N/A means incompleted
Note on H3: KienNT: You have updated the function in the last iteration?
Note on J3: KienNT: The name of section in the SRS (software requirement specification) document
Note on K3: KienNT: The name of section in the SDS (software design specification) document

## Iter1
Iteration 1
# | Function/Screen | Feature | Level | Function/Screen Details | In Charge | Status | Notes
1 | User Login | Common | Simple | This is scrren when user want to access the important part of the website have to do. User access with their created account or can go ahead and create a new one | HungTHHE140042 | Done
2 | User Register | Common | Simple | This is the screen user want to access other parts of the website but does not already have username and password. Therefore they will have to enter their new username and password, come along with email and phone number | HungTHHE140043 | Done
3 | Verify new register | Common | Simple |  | HungTHHE140043 | Done
4 | Post dashboard | Admin | Medium | Blog is the post who created by the marketing team, the advertise about new product, new promotion to user. Or just simply review about a product. With a title, author, date, thumbnail and a briefly descript about the product | SonTNSE04223 | Doing
5 | Homepage | Common | Medium | Homepage display hot product, new product, latest blog,… | DinhNLHE140992 | Doing
6 | Change Password | Common | Simple | This is screen to user change their password | HungDQHE140061 | Doing
7 | Profile Detail | Common | Simple | This is a screen which allows user to view their own profile information, including all personal information & avatar image. User can change profile detail by click in edit button to redirect in edit profile screen. User can view order history by click in order history button | HungDQHE140062 | Doing
8 | Products List | Common | Simple | Show the paginated list of products (include products' id, thumbnail, title, category, list price, sale price, featured, and status information): - The user can filter the product by category, status or search by title, brief info - Sortable by title, category, list price, sale price, featured, or status - From each product, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new product | SangNQHE140244 | Doing
9 | Product Details | Common | Simple | Show detailed product information (thumbnail, category, title, brief information, attached images, description, quantity, list price, sale price, flag to turn the featurning on/off, status), | SangNQHE140245 | Doing
10 | Users List | Admin | Simple | Show the paginated list of registered users (include users' id, full name, gender, email, mobile, role, status): - The admin can filter the users by gender, role, status - Allow the admin to seach users by full name, email, mobile - The list is sortable by id, fullname, gender, email, mobile, role, status - From each user, the admin can choose to view or edit it - The page also have the button/link that allows the admin to add new user | LongTNHE140954 | Doing
11 | User Details | Admin | Simple | Show detailed user information (avatar, full name, gender, email, mobile, role, address, status), from that allow the user to add new, view or edit user information - After adding, new generated login password would be email to the new user - The admin can only edit/update the role and status of the user | LongTNHE140955 | Doing

## Iter2
Iteration 2
# | Function/Screen | Feature | Level | Function/Screen Details | In Charge | Status | Notes
12 | Product Dashboard | Admin | Complex |  | HungTHHE140042 | Doing
13 | Post list | Admin | Simple |  | SonTNSE04223 | Doing
14 | Post detail | Admin | Simple |  | SonTNSE04223 | Doing
15 | CMS Dashboard | Staff | Medium |  | DinhNLHE140992 | Doing
16 | Product Review | Common | Medium |  | HungDQHE140061 | Doing
17 | My Cart | Common | Simple |  | SangNQHE140245 | Doing
18 | Add to Cart | Common | Medium |  | SangNQHE140245 | Doing
19 | FAQ dashboard | Admin | Medium |  | LongNTHE140954 | Doing

## Iter3
Iteration 3
# | Function/Screen | Feature | Level | Function/Screen Details | In Charge | Status | Notes
20 | User Reset Pasword | Common | Medium | This is the screen for user that have already created an acoount but does not remember username or password, they can enter the email and the website will send them new user and password via email | HungTHHE140042 | Doing
21 | Post dashboard | Admin | Medium |  | SonTNSE04223 | Doing
22 | Categories Dashboard | Admin | Simple |  | DinhNLHE140992 | Doing
15 | FAQ list | Common | Simple |  | HungDQHE140061 | Doing
16 | FAQ detail | Common | Simple |  | HungDQHE140062 | Doing
24 | Notifications Dashboard | Admin | Medium |  | SangNQHE140245 | Doing
25 | Cart Completion | Admin | Medium |  | LongNTHE140954 | Doing

## Iter4
Iteration 4
# | Function/Screen | Feature | Level | Function/Screen Details | In Charge | Status | Notes
26 | About us | Common | Simple |  | HungTHHE140042 | Doing
27 | Order history | Common | Simple |  | SonTNSE04223 | Doing
28 | Order history detail | Common | Simple |  | SonTNSE04223 | Doing
29 | User Authorization | Security | Complex |  | DinhNLHE140992 | Doing
30 |  |  |  |  | HungDQHE140061 | Doing
31 | Notification list | Common | Simple |  | SangNQHE140245 | Doing
32 | Notification detail | Common | Simple |  | SangNQHE140245 | Doing
33 | Order Dashboard | Admin | Medium |  | LongNTHE140954 | Doing