## Backlog
Final Product Backblog
# | Function/Screen | Feature | Function/Screen Details | Level* | In charge | Actual | Updated? | Details on update | SRS Section | SDS Section
1 | User Login | Common | This is scrren when user want to access the important part of the website have to do. User access with their created account | Simple | HungTHHE140042 | Iter1 | No
2 | User Register | Common | This is the screen user want to access other parts of the website but does not already have username and password. Therefore they will have to enter their new username and password, come along with email | Simple | HungTHHE140043 | Iter1 | No
3 | Verify new register | Common | After registed success, a link by an email will send to user registed email. Access email to verify account. | Simple | HungTHHE140043 | Iter1 | No
4 | Post dashboard | Marketing | Post Dashboard is the post who created by the marketing team, the advertise about new product, new promotion to user. Or just simply review about a product. With a title, author, date, thumbnail and detail image and a briefly descript about the product - Allow the admin/marketing to search post by post's id, author, title, content - The list is sortable by post' id, author, title, content - From each post, the admin/marketing can choose to edit it - The page also have the button that allows the admin/marketing to create new post and delete post | Medium | SonTNSE04223 | Iter1 | No
5 | Homepage | Common | Homepage is welcome page, its display top discount product, newest product, popular products and latest post. Beside, header will change between user logged or not | Medium | DinhNLHE140992 | Iter1 | No
6 | Change Password | Common | This is screen to user change their password | Simple | HungDQHE140061 | Iter1 | No
7 | Profile Detail | Common | This is a screen which allows user to view their own profile information, including all personal information. | Simple | HungDQHE140062 | Iter1 | No
8 | Products List | Common | Show the paginated list of products (include products' id, thumbnail, title, category, list price, sale price). The user can filter the product by category, price or search by title | Simple | SangNQHE140244 | Iter1 | No
9 | Product Details | Common | Show detailed product information (thumbnail, title, attached images, description, quantity, list price, sale price), | Simple | SangNQHE140245 | Iter1 | No
10 | Users List | Admin | Show the paginated list of registered users (include users' id, username, password, email, role, status): - Allow the admin to search users by username, email, id - The list is sortable by users' id, username, password, email, role, status - The page also have the button that allows the admin to add new user and delete user | Simple | LongNTHE140954 | Iter1 | No
11 | User Details | Admin | Show detailed user information (user's id, username, email, mobile, role, status), from that allow the user to add new, view or edit user information - The admin can edit all information of the user | Simple | LongNTHE140955 | Iter1 | No
12 | Product Management | Seller | Product management is control by the seller team, Create new product, edit detail product. each product has title, category, original price, discount price, date ,thumbnail and detail image and a briefly descript about the product - Allow the admin/ seller to search product by product id, title, detail product - The list is sortable by product id, title and date - For each product, the admin/seller can choose to edit it - The page also have the button that allows the admin/seller to create new product and delete product | Complex | HungTHHE140042 | Iter2 | No
13 | Post list | Common | Show the paginated list of posts (include post's id, author, title, content, image, date). | Simple | SonTNSE04223 | Iter2 | No
14 | Post detail | Common | Show detailed post information (post's id, author, title, content, image, date), | Simple | SonTNSE04223 | Iter2 | No
15 | CMS Dashboard | Admin - Seller - Marketing | Analysis: Total product revenue, Product revenue in this month, Total success order, Amount of current pending order Revenue by day chart, Category have product success order chart | Simple | DinhNLHE140992 | Iter2 | No
16 | Product Review | Customer - Seller - Marketing | At product detail page, user can comment to review about product. Seller or Marketing can reply user's review. | Medium | HungDQHE140061 | Iter2 | No
17 | My Cart | Common | List all product user has add to cart. User also increase, decrese product amout or delete them. | Simple | SangNQHE140245 | Iter2 | No
18 | Add to Cart | Common | After click button "Add to cart" from Product page, that product will has been add to user cart. | Medium | SangNQHE140245 | Iter2 | No
19 | FAQ Management | Marketing | FAQs Dashboard is the FAQ who created by the marketing team, its frequently asked questions. Summary of questions from product review, marketing team will create FAQs - Allow the admin/marketing to search post by faq's id, author, title, content - The list is sortable by faq's id, author, title, content - From each post, the admin/marketing can choose to edit it - The page also have the button that allows the admin/marketing to create new FAQ and delete FAQ | Medium | LongTNHE140954 | Iter2 | No
20 | User Reset Pasword | Common | This is the screen for user that have already created an acoount but does not remember username or password, they can enter the email and the website will send them new user and password via email | Simple | HungTHHE140042 | Iter3 | No
21 | Categories Management | Seller | Category Management is manager by the seller team. - Allow the admin/seller to search category by category's id, category name - The list is sortable by category's id, category name - From each category, the admin/seller can choose to edit it - The page also have the button that allows the admin/seller to create new Category and delete Category | Simple | SonTNSE04223 | Iter3 | No
22 | Promotion Code Management | Seller | Promotion Management is manager by the seller team. - Allow the admin/seller to search Promotion Code by promotion's id, promotion code - The list is sortable by promotion's id, promotion code - From each promotion code, the admin/seller can choose to edit it - The page also have the button that allows the admin/seller to create new Promotion code and delete Promotion code | Medium | DinhNLHE140992 | Iter3 | No
23 | FAQ list | Common | At FAQ page in nav bar, user can read all of FAQ. | Simple | HungDQHE140061 | Iter3 | No
24 | FAQ detail | Common | Each FAQ title, it will have dropdown button in the next title. User can click on it to read detail FAQ | Simple | HungDQHE140062 | Iter3 | No
25 | Cart Completion (Checkout) | Common | At Cart page, after shopping, customers can click "Check Out" button to completion them cart. In Checkout page, customers can double check them products. Also customers can apply Promotion code to decrease them price order. | Medium | SangNQHE140245 | Iter3 | No
26 | Payment | Common | When click "Payment" button at Checkout page, Customer's order will be recognized by the system. At the same time Payment page will appear to display payment information, and money customer must be pay. | Simple | SangNQHE140245 | Iter3 | No
27 | Notifications Management | Marketing | Notification Management is manager by the marketing team. - Allow the admin/marketing to search notification by notification's id, title, content, time - The list is sortable by notification's id, title, content, time - From each notification, the admin/marketing can choose to send it - The page also have the button that allows the admin/seller to create new Notification and delete Category | Medium | LongTNHE140954 | Iter3 | No
28 | About us | Common | About Us page will display information,address, contact point of our team. | Simple | HungTHHE140042 | Iter4 | No
29 | Auto send email | Common | When customer click Subcribe checkbox in Profile page, them will be receive all of notification about new product, new post, new promotion to their email. | Simple | HungTHHE140042 | Iter4 | No
30 | Order history | Common | At Order History, cusomters can view their order history and it status | Simple | SonTNSE04223 | Iter4 | No
31 | Order history detail | Common | When click to an Order, Order detail will appear to display that order detail | Simple | SonTNSE04223 | Iter4 | No
32 | User Authorization | Security | Authorization all page and all url in project. Accounts do not have permision, it will can not access some page/url | Complex | DinhNLHE140992 | Iter4 | No
33 | Email Management | Marketing | Email Management is manager by the marketing team. - Allow the admin/seller to search email notification by email's id, title, content, status, date - The list is sortable by email's id, title, content, status, date - From each category, the admin/seller can choose to send it - The page also have the button that allows the admin/seller to create new Email Notification and delete Email Notification | Medium | HungDQHE140061 | Iter4 | No
34 | Notification list | Common | At Notification page, it will list all notification with each customer | Simple | LongTNHE140954 | Iter4 | No
35 | Notification detail | Common | Each notification, when user click on it title, Notification detail will appear to display notificaition | Simple | LongTNHE140954 | Iter4 | No
36 | Order Management | Seller | Order Management is manager by the seller team. - Allow the admin/seller to search order by order's id, total price, note, status, date, promotion - The list is sortable by order's id, total price, note, status, date, promotion - From each category, the admin/seller can choose to edit and view detail it - The page also have the button that allows the admin/seller to delete Order | Medium | SangNQHE140245 | Iter4 | No
Note on G3: KienNT: Actual iteration when you have completed the function; N/A means incompleted
Note on H3: KienNT: You have updated the function in the last iteration?
Note on J3: KienNT: The name of section in the SRS (software requirement specification) document
Note on K3: KienNT: The name of section in the SDS (software design specification) document

## Iter1
Iteration 1
# | Function/Screen | Feature | Level | Function/Screen Details | In Charge | Status | Notes
1 | User Login | Common | Simple | This is scrren when user want to access the important part of the website have to do. User access with their created account | HungTHHE140042 | Done
2 | User Register | Common | Simple | This is the screen user want to access other parts of the website but does not already have username and password. Therefore they will have to enter their new username and password, come along with email | HungTHHE140043 | Done
3 | Verify new register | Common | Simple | After registed success, a link by an email will send to user registed email. Access email to verify account. | HungTHHE140043 | Done
4 | Post Management | Marketing | Medium | Post Dashboard is the post who created by the marketing team, the advertise about new product, new promotion to user. Or just simply review about a product. With a title, author, date, thumbnail and detail image and a briefly descript about the product - Allow the admin/marketing to search post by post's id, author, title, content - The list is sortable by post' id, author, title, content - From each post, the admin/marketing can choose to edit it - The page also have the button that allows the admin/marketing to create new post and delete post | SonTNSE04223 | Done
5 | Homepage | Common | Medium | Homepage is welcome page, its display top discount product, newest product, popular products and latest post. Beside, header will change between user logged or not | DinhNLHE140992 | Done
6 | Change Password | Common | Simple | This is screen to user change their password | HungDQHE140061 | Done
7 | Profile Detail | Common | Simple | This is a screen which allows user to view their own profile information, including all personal information. | HungDQHE140062 | Done
8 | Products List | Common | Simple | Show the paginated list of products (include products' id, thumbnail, title, category, list price, sale price). The user can filter the product by category, price or search by title | SangNQHE140244 | Done
9 | Product Details | Common | Simple | Show detailed product information (thumbnail, title, attached images, description, quantity, list price, sale price), | SangNQHE140245 | Done
10 | Users List | Admin | Simple | Show the paginated list of registered users (include users' id, username, password, email, role, status): - Allow the admin to search users by username, email, id - The list is sortable by users' id, username, password, email, role, status - The page also have the button that allows the admin to add new user and delete user | LongTNHE140954 | Done
11 | User Details | Admin | Simple | Show detailed user information (user's id, username, email, mobile, role, status), from that allow the user to add new, view or edit user information - The admin can edit all information of the user | LongTNHE140955 | Done

## Iter2
Iteration 2
# | Function/Screen | Feature | Level | Function/Screen Details | In Charge | Status | Notes
12 | Product Management | Seller | Complex | Product management is control by the seller team, Create new product, edit detail product. each product has title, category, original price, discount price, date ,thumbnail and detail image and a briefly descript about the product - Allow the admin/ seller to search product by product id, title, detail product - The list is sortable by product id, title and date - For each product, the admin/seller can choose to edit it - The page also have the button that allows the admin/seller to create new product and delete product | HungTHHE140042 | Done
13 | Post list | Common | Simple | Show the paginated list of posts (include post's id, author, title, content, image, date). | SonTNSE04223 | Done
14 | Post detail | Common | Simple | Show detailed post information (post's id, author, title, content, image, date), | SonTNSE04223 | Done
15 | CMS Dashboard | Admin - Seller - Marketing | Simple | Analysis: Total product revenue, Product revenue in this month, Total success order, Amount of current pending order Revenue by day chart, Category have product success order chart | DinhNLHE140992 | Done
16 | Product Review | Customer - Seller - Marketing | Medium | At product detail page, user can comment to review about product. Seller or Marketing can reply user's review. | HungDQHE140061 | Done
17 | My Cart | Common | Simple | List all product user has add to cart. User also increase, decrese product amout or delete them. | SangNQHE140245 | Done
18 | Add to Cart | Common | Medium | After click button "Add to cart" from Product page, that product will has been add to user cart. | SangNQHE140245 | Done
19 | FAQ Management | Marketing | Medium | FAQs Dashboard is the FAQ who created by the marketing team, its frequently asked questions. Summary of questions from product review, marketing team will create FAQs - Allow the admin/marketing to search post by faq's id, author, title, content - The list is sortable by faq's id, author, title, content - From each post, the admin/marketing can choose to edit it - The page also have the button that allows the admin/marketing to create new FAQ and delete FAQ | LongTNHE140954 | Done

## Iter3
Iteration 3
# | Function/Screen | Feature | Level | Function/Screen Details | In Charge | Status | Notes
20 | User Reset Pasword | Common | Simple | This is the screen for user that have already created an acoount but does not remember username or password, they can enter the email and the website will send them new user and password via email | HungTHHE140042 | Done
21 | Categories Management | Seller | Simple | Category Management is manager by the seller team. - Allow the admin/seller to search category by category's id, category name - The list is sortable by category's id, category name - From each category, the admin/seller can choose to edit it - The page also have the button that allows the admin/seller to create new Category and delete Category | SonTNSE04223 | Done
22 | Promotion Code Management | Seller | Medium | Promotion Management is manager by the seller team. - Allow the admin/seller to search Promotion Code by promotion's id, promotion code - The list is sortable by promotion's id, promotion code - From each promotion code, the admin/seller can choose to edit it - The page also have the button that allows the admin/seller to create new Promotion code and delete Promotion code | DinhNLHE140992 | Done
23 | FAQ list | Common | Simple | At FAQ page in nav bar, user can read all of FAQ. | HungDQHE140061 | Done
24 | FAQ detail | Common | Simple | Each FAQ title, it will have dropdown button in the next title. User can click on it to read detail FAQ | HungDQHE140062 | Done
25 | Cart Completion (Checkout) | Common | Medium | At Cart page, after shopping, customers can click "Check Out" button to completion them cart. In Checkout page, customers can double check them products. Also customers can apply Promotion code to decrease them price order. | SangNQHE140245 | Done
26 | Payment | Common | Simple | When click "Payment" button at Checkout page, Customer's order will be recognized by the system. At the same time Payment page will appear to display payment information, and money customer must be pay. | SangNQHE140245 | Done
27 | Notifications Management | Marketing | Medium | Notification Management is manager by the marketing team. - Allow the admin/marketing to search notification by notification's id, title, content, time - The list is sortable by notification's id, title, content, time - From each notification, the admin/marketing can choose to send it - The page also have the button that allows the admin/seller to create new Notification and delete Category | LongTNHE140954 | Done

## Iter4
Iteration 4
# | Function/Screen | Feature | Level | Function/Screen Details | In Charge | Status | Notes
26 | About us | Common | Simple | About Us page will display information,address, contact point of our team. | HungTHHE140042 | Doing
27 | Auto send email | Common | Simple | When customer click Subcribe checkbox in Profile page, them will be receive all of notification about new product, new post, new promotion to their email. | HungTHHE140042 | Doing
28 | Order history | Common | Simple | At Order History, cusomters can view their order history and it status | SonTNSE04223 | Doing
29 | Order history detail | Common | Simple | When click to an Order, Order detail will appear to display that order detail | SonTNSE04223 | Doing
30 | User Authorization | Security | Complex | Authorization all page and all url in project. Accounts do not have permision, it will can not access some page/url | DinhNLHE140992 | Doing
31 | Email Management | Marketing | Medium | Email Management is manager by the marketing team. - Allow the admin/seller to search email notification by email's id, title, content, status, date - The list is sortable by email's id, title, content, status, date - From each category, the admin/seller can choose to send it - The page also have the button that allows the admin/seller to create new Email Notification and delete Email Notification | HungDQHE140061 | Doing
32 | Notification list | Common | Simple | At Notification page, it will list all notification with each customer | LongTNHE140954 | Doing
33 | Notification detail | Common | Simple | Each notification, when user click on it title, Notification detail will appear to display notificaition | LongTNHE140954 | Doing
34 | Order Management | Seller | Medium | Order Management is manager by the seller team. - Allow the admin/seller to search order by order's id, total price, note, status, date, promotion - The list is sortable by order's id, total price, note, status, date, promotion - From each category, the admin/seller can choose to edit and view detail it - The page also have the button that allows the admin/seller to delete Order | SangNQHE140245 | Doing